## Slide 1
CDR (2023.04)
Electrical Power System
  Hardware
    PCDU
    Solar Cell, Panel
    Battery
  Test plan

## Slide 2: Level 1: Electrical Power System
Level 2 | Level 3 | DAYS
 |  | 0
 |  | 0
 |  | 0
 |  | 0
 |  | 0
 |  | 0

## Slide 3
1월 스케줄
2023-02-01
EPS
4
향후 계획
일 | 월 | 화 | 수 | 목 | 금 | 토 | 
 |  |  |  |  |  | 14 | 
15 | 16 | 17 | 18 | 19 | 20 | 21 | 
 | Hardware (PCDU) | Hardware (PCDU) | Hardware (PCDU) | Hardware (PCDU) | Hardware (PCDU) |  | 
22 | 23 | 24 | 25 | 26 | 27 | 28 | 
 |  |  | Hardware (Battery) | Hardware (Battery) | Hardware (Solar Panel, Cell) |  | 
29 | 30 | 31 |  |  |  |  | 
 | 실험 계획 & 실험 리스트 작성 | 실험 계획 & 실험 리스트 작성 |  |  |  |  | 

## Slide 4
2월 스케줄
2023-02-01
EPS
5
향후 계획
일 | 월 | 화 | 수 | 목 | 금 | 토 | 
 |  |  | 1 | 2 | 3 | 4 | 
 |  |  | 실험 계획 & 실험 리스트 작성 | 실험 계획 & 실험 리스트 작성 | 실험 계획 & 실험 리스트 작성 |  | 
5 | 6 | 7 | 8 | 9 | 10 | 11 | 
 | 실험 시작 |  |  |  |  |  | 
12 | 13 | 14 | 15 | 16 | 17 | 18 | 
19 | 20 | 21 | 22 | 23 | 24 | 25 | 
26 | 27 | 28 |  |  |  |  | 

## Slide 5
3월 스케줄
2023-02-01
EPS
6
향후 계획
일 | 월 | 화 | 수 | 목 | 금 | 토 | 
 |  |  | 1 | 2 | 3 | 4 | 
5 | 6 | 7 | 8 | 9 | 10 | 11 | 
12 | 13 | 14 | 15 | 16 | 17 | 18 | 
 | CDR 자료 만들기 |  |  |  |  |  | 
19 | 20 | 21 | 22 | 23 | 24 | 25 | 
 | CDR 자료 만들기 |  |  |  |  |  | 
26 | 27 | 28 | 29 | 30 | 31 |  | 
 | CDR 자료 제출 |  |  |  |  |  | 

## Slide 6
4월 스케줄
2023-02-01
EPS
7
향후 계획
일 | 월 | 화 | 수 | 목 | 금 | 토 | 
 |  |  | 1 | 2 | 3 | 1 | 
 |  |  | CDR |  |  |  | 
5 | 6 | 7 | 8 | 9 | 10 | 11 | 
12 | 13 | 14 | 15 | 16 | 17 | 18 | 
19 | 20 | 21 | 22 | 23 | 24 | 25 | 
26 | 27 | 28 | 29 | 30 | 31 |  | 

## Slide 7
CDR까지 준비할 내용
2023-02-01
EPS
3
향후 계획
주요 목표 | 착수 | 마감 | 진행 | 비고
EPS 하드웨어 숙지하기 (PCDU) | 2023-01-08 | 2023-01-24 | 80% | 
EPS 하드웨어 숙지하기 (Battery) | 2023-01-25 | 2023-01-26 | 80% | 
EPS 하드웨어 숙지하기 (Solar Cell, Panel) | 2023-01-27 | 2023-01-27 | 70% | 
실험 계획 & 실험 리스트 작성 | 2023-01-30 | 2023-02-03 | 10% | 
실험 시작 | 2023-02-06 | 2023-03-10 | 0% | 
CDR 자료 준바 | 2023-03-13 | 2023-03-31 | 0% | 

## Slide 8
2023-02-01
EPS
10
실험계획 – Test
Test List
  BCR test
  PCM test
  Battery charging / discharging
  Get I2C telemetry
  Solar Array
Set Equipment
  Power supply
  Multi-meter
  Electronic Load
  I2C communicate board
  Under ESD protection
  In clean-booth

## Slide 9
2023-02-01
EPS
10
실험계획 – Requirements : 1U

## Slide 10
2023-02-01
EPS
10
실험계획 – Requirements : EPS Module

## Slide 11
2023-02-01
EPS
10
실험계획 – Requirements : Battery

## Slide 12
2023-02-01
EPS
10
실험계획 – Requirements : Solar Panel

## Slide 13
2023-02-01
EPS
10
실험계획 - Product Specification
3U Solar Array
Gomspace
AAC Clyde Space
AAC Clyde Space
MIMAN
HYVRID

## Slide 14
2023-02-01
EPS
10
실험계획 – PCM
PCM (Power Conditioning Module)
  1) 3.3, 5 V, unregulated bus regulator
    Sweep load current up
    Voltage check per load current
    Peak-to-peak noise of DC
  2) 12 V bus regulator (2U only)
  3) Battery under-voltage shutdown
Test Setup
Power Supply | Electrical load | Oscilloscope
Connect pin#36 with 7.74 V (typ.) | Connect with PCM pin and change load current (50 ~ 1500 mA) | Connect with electrical load node
EPS
PC104
Oscilloscope
Electric load
Power supply
Multi-meter

## Slide 15
2023-02-01
EPS
10
실험계획 – PCM
Charge Mode
  MPPT mode
    Before battery voltage reaches to EoC
      EoC level: 8.26 V
    Check voltage level during charging
      7.0 ~ 8.0 V
Power
Supply
Oscilloscope
Power
Supply
Electric load
Multi-meter (V)
BAT-EPS

## Slide 16
2023-02-01
EPS
10
실험계획 – PCM
Load Electric Power and Monitor Battery Voltage
  Convert C rate to current value
    30 Wh Battery capacity: 3.435 Ah @20 degree
    Recommended maximum C/2
      C/2: 1.718 A loaded by electric load
      C/5: 0.687 A loaded by electric load
      C/10: 0.344 A loaded by electric load
      C/15: 0.229 A loaded by electric load
Tune Current load
Check Voltage
Check Time